## Tabelle1
Section | Feature | Priority | Estimated hours | estimated delivery | actual completion
Framework | error msg ausgeben bei errno != 0 SQL Fail
grundsätzliches mysql error handling ; größtenteils drin, passt erstmal so
memcache: fehlende items nachziehen
styles
languages
language functionality: wenn eingeloggt dann auch in DB ändern; kürzel mit nach JS übertragen, nicht 1, 2…
indizes datenbank prüfen
alle strings in language files auslagern, auch in DB checken (z.b. checklist items) bzw. in code schon fertig integrieren name_LANG
mysql_real_escape_string für alle user eingaben die in die db gehen
implement trigger to refresh all memcache items
in functions auslagern wo möglich
htaccess expand ohne index
code kommentieren
grundsätzlich DB abfragen minimal halten / cachen, auch text queries
Bugs | highlight text, bg and color fix
diary: nach eintrag wird liste zweimal angezeigt
Design | css styles und tpl files aufräumen
Login | redirect bei nicht login rausnehmen
passwort speichern box auch im chrome
forgot password
Registration | phpmailer eins raus |  |  |  | 6.9.
Burns Depression Checklist | form questions
inserting it DB
overview page (detailed view)
information
progress over time
Dysfunctional Attitude Scale | form questions
inserting it DB
overview page
select box 1 item fix
was ist bei 0 items!?
information
suggestions for improvement areas
memcache graph data
Average Variety Score | to be specified
Analyses overview | combine all 3 results
Daily Diary | view
insert
page view
archive
“Guidelines”/Rules | to be specified; turn negative in positive ones
Goals | to be specified; how does it emerge from the analyses and rules
update when goals have been achieved
Activities | ask what user is regulary doing
let him track when to do activities last time etc
Distorted thoughts | enter new ones ajax
update when thought has been continously eliminated
progress view (3 of 10 thoughts eliminated; ...)
Happidentifier | to be specified; what makes u happy administration
update when last done
My Dreams | add new ones
output on profile
Overview page | profile information / myself
mash all data up; tracking & outputing
General stuff | landing page information
recommendations
links (fb, ...)
imprint
contact
Forum
Statistics
Feedback
Expert Chat
Blog / Information | pinterest style + share + comment funktion
Feedback